## Table 1
Monthwise ABP: (26-27)
(UNIT : '000 T)
SL. | PARTICULARS | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | TOTAL
NO. |  | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2026-27
1 | Av. Oven Pushing/Day(Nos) :
| Batts. 1-8 | 367 | 371 | 373 | 370 | 370 | 357 | 315 | 324 | 324 | 324 | 324 | 324 | 345
| Batt. 9 & 10 | 155 | 160 | 160 | 160 | 160 | 160 | 162 | 162 | 162 | 162 | 162 | 162 | 161
| Batt. 11 | 77 | 77 | 77 | 48 | 77 | 77 | 88 | 88 | 88 | 88 | 88 | 88 | 80
| Eq.Oven Pushing | 786 | 799 | 801 | 745 | 798 | 785 | 766 | 775 | 775 | 775 | 775 | 775 | 780
2 | B.F.Coke(Dry) | 269 | 282 | 274 | 263 | 282 | 268 | 270 | 265 | 274 | 274 | 247 | 274 | 3240
3 | SINTER : SP - II | 259 | 267 | 242 | 269 | 269 | 242 | 258 | 257 | 269 | 258 | 241 | 269 | 3100 | 3100
| : SP - III | 568 | 593.2 | 568 | 497 | 534 | 573.4 | 588.4 | 573.4 | 588.4 | 593.4 | 529.4 | 593.4 | 6800 | 6800
| SINTER Total | 827 | 860.2 | 810 | 766 | 803 | 815.4 | 846.4 | 830.4 | 857.4 | 851.4 | 770.4 | 862.4 | 9900 | 9900
4 | Hot Metal : BF 1-7 | 301 | 311 | 301 | 311 | 296 | 285 | 311 | 301 | 311 | 284 | 280 | 311 | 3603 | 3603
| : BF 8 | 257 | 266 | 257 | 179 | 266 | 257 | 266 | 257 | 221 | 266 | 239 | 266 | 2997 | 2997
| Total HM | 558 | 577 | 558 | 490 | 562 | 542 | 577 | 558 | 532 | 550 | 519 | 577 | 6600 | 6600
5 | Cold Pig Iron | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Crude Steel : SMS-II | 228 | 219 | 201 | 200 | 214 | 201 | 216 | 233 | 181 | 216 | 202 | 214 | 2525 | 2525
| : SMS-III | 316 | 345 | 345 | 279 | 335 | 329 | 348 | 313 | 339 | 322 | 306 | 348 | 3925 | 3925
| Total | 544 | 564 | 546 | 479 | 549 | 530 | 564 | 546 | 520 | 538 | 508 | 562 | 6450 | 6450
7 | SMS-II | [13 empty] | 0
| Cast Blooms | 63 | 67 | 65 | 68 | 68 | 65 | 68 | 67 | 68 | 68 | 65 | 68 | 800 | 800
| Cast Slabs | 165 | 152 | 136 | 132 | 146 | 136 | 148 | 166 | 113 | 148 | 137 | 146 | 1725 | 1725
| Total | 228 | 219 | 201 | 200 | 214 | 201 | 216 | 233 | 181 | 216 | 202 | 214 | 2525 | 2525
8 | SMS-III | [13 empty] | 0
| Cast Blooms : CV-1/CV-2 | 104 | 110 | 108 | 97 | 112 | 97 | 115 | 126 | 121 | 90 | 100 | 116 | 1296 | 1296
| Cast Billets : 105² | 73 | 110.7 | 106.6 | 110.6 | 110.6 | 106.5 | 109.7 | 105.6 | 109.6 | 109.6 | 97.7 | 109.8 | 1260 | 1260
| Cast Billets : 150² | 139 | 124.3 | 130.4 | 71.4 | 112.4 | 125.5 | 123.3 | 81.4 | 108.4 | 122.4 | 108.3 | 122.2 | 1369 | 1369
| Total Cast | 316 | 345 | 345 | 279 | 335 | 329 | 348 | 313 | 339 | 322 | 306 | 348 | 3925 | 3925
9 | Saleable Steel : | [13 empty] | 0
| RSM : Rails | 51 | 53 | 51 | 53 | 53 | 37 | 53 | 51 | 53 | 53 | 49 | 53 | 610 | 610
| URM : Rails | 80 | 99 | 97 | 97 | 100 | 96 | 98 | 96 | 99.7 | 82 | 91.7 | 99.6 | 1136 | 1136
| Merchant Mill | 45 | 61 | 58 | 61 | 61 | 58 | 61 | 58 | 61 | 61 | 54 | 61 | 700 | 700
| Wire Rods | 20 | 44 | 43.4 | 44.4 | 44.4 | 43.2 | 44 | 43 | 44.4 | 44.4 | 40.4 | 44.4 | 500 | 500
| Bars & Rods Mill | 97 | 101 | 97 | 80 | 100.6 | 97 | 101 | 34 | 100.7 | 100.7 | 90 | 101 | 1100 | 1100
| Plate Mill | 116 | 120 | 95 | 123 | 123 | 119 | 123 | 119 | 47 | 120 | 105 | 120 | 1330 | 1330
| Total Finished Steel | 409 | 478 | 441 | 458 | 482 | 450 | 480 | 401.2 | 406 | 461.4 | 430 | 479.4 | 5376 | 5376
10 | Semis for sale | [13 empty] | 0
| SMS-II : Slabs | 30 | 6 | 20 | 0 | 3 | 5 | 5 | 27 | 50 | 19 | 16 | 9 | 190 | 190
| SMS-II/III : Blooms | 15 | 10 | 9 | 0 | 11 | 15 | 17 | 30 | 20 | 10 | 9 | 14 | 160 | 160
| SMS-III : Billets | 21 | 12 | 16 | 1 | 9 | 25 | 17 | 45 | 21 | 15 | 13 | 15 | 210 | 210
| Total Semis | 66 | 28 | 45 | 1 | 23 | 45 | 39 | 102 | 91 | 44 | 38 | 38 | 560 | 560
11 | Total Saleable Steel | 475 | 506 | 486 | 459 | 505 | 495 | 519.4 | 503.4 | 497 | 505.2 | 468 | 517 | 5936 | 5936
0
12 | Prime Rail Prod : RSM | 42 | 44 | 42 | 44 | 44 | 30.5 | 43.8 | 41.9 | 43.8 | 44 | 41 | 44 | 505 | 505
| : URM | 77 | 95 | 93 | 93 | 96 | 91 | 93 | 91 | 96 | 78 | 88 | 96 | 1087 | 1087
| Total | 119 | 139 | 135 | 137 | 140 | 121.5 | 136.8 | 132.9 | 139.8 | 122 | 129 | 140 | 1592 | 1592

## Table 2
Major Repair Plan: (26-27)
DEPTT. | Machines | Apr'26 | May'26 | Jun'26 | Jul'26 | Aug'26 | Sep'26 | Oct'26 | Nov'26 | Dec'26 | Jan'27 | Feb'27 | Mar'27 | Remarks
COCCD | Batt-1 | [12 empty] | COB #1 Down from Sept, after COB #8 Commissioning.
| Batt-3 | [12 empty] | COB #3 Down from Sept, after COB #11 repair completion.
Batt-6
| Batt-8 | [12 empty] | COB # 6 Cold repair from April, after COB#4 commissioning.
| Batt-11 |  |  |  | 10 | [8 empty] | GCM & battery equipment replacement, Liquor line replacement
OHP | Wagon Tippler-6 |  |  |  | 10
SP-2 | M/c-1 |  |  | 9 | [9 empty] | Vacuum line repair/ changing, Sinter Machine track sealing changing, Sinter Cooler carriage changing, SMD shell changing/ SS LINER fixing/ changing, Hot screen changing, Single roll crusher changing, Base frame changing, Exhauster Fan changing/ Casing repair, Raw mix hopper both to repair / liner changing.
| M/c-2 | [5 empty] | 9
| M/c-3 | [6 empty] | 6
| M/c-4 | [9 empty] | 6
SP-3 | M/c-1 |  |  |  |  | 7 | [7 empty] | Sinter machine rail & crusher guide liner change.
| M/c-2 |  |  |  | 10 | [8 empty] | Machine DE and TE sprocket gear rim replacement and track alignment
BFs | No-4 |  |  |  |  | 5 | [7 empty] | BLT Chute Changing + Shot Creting
| No-6 | [5 empty] | 5 | [6 empty] | BLT Chute Changing+ Gear Box Inspection
| No-7 | [9 empty] | 6 |  |  | Shot Creting + Gearbox Changing
| No-8 |  |  |  | 9 |  |  |  |  | 4 |  |  |  | - Shot creting + Repair In HBM + Replacement of Stove No 3 compensator + HBV 3
SMS2 | Conv-A |  | 45 | [10 empty] | Vessel & drive replacement (Project jobs) & Campaign repair
| Conv-B |  |  |  |  | 11 | [7 empty] | Campaign repair & vessel relining
Conv-C
| Caster-3 | 11 |  |  |  |  | 45 | [6 empty] | Campaign repair & relining,
SMS3 | BOF-1* |  |  |  |  | 25 | [7 empty] | BOF Relining/
| BOF-2 |  |  |  | 11 | [8 empty] | Campaign repair & vessel relining
BOF-3
| CK-1 | 11 | [11 empty] | Campaign repair & vessel relining
| CK-2 |  |  |  | 10
| CV-1 |  |  |  |  | 11
Mills | RSM | [5 empty] | 10 | [6 empty] | 2D Internal , pinion shaft with babbit changing,
URM
| MMILL | 7 | [8 empty] | 7 |  |  | Mill Equipments + RHF repair,
| WRM | 18 | [11 empty] | Housing less stand commissioning in 4 strands,
| BRM |  |  |  | 7 |  |  |  | 20 |  |  |  |  | Replacement of Furnace Skids and Posts with refractory,
| Plate Mill |  |  | 6 | [5 empty] | 20 |  |  |  | Dosmantling & (Hot Leveller commissioning, SAC commissioning)

## Table 3
IMPORTANT PLAN PARAMETERS
Particulars |  | Unit | Plan | Particulars | Unit | Plan | Particulars | Unit | Plan
COKE OVENS & COAL CHEMICALS : |  |  |  | BLAST FURNACES : |  |  | STEEL MELTING SHOP-II :
Consumption Per Tonne of Hot Metal
Dry Charge per Oven
Coal Blend Composition |  | T | 16.5 | Coke Rate (Dry) | Kg | 407 | Consumption per Tonne of Cast Steel
Indigenous : | PCC | % | 13 | CDI rate (Dry) | Kg | 125 | Steel scrap | Kg | 74
| MCC | % | 2 | Total Fuel Rate | Kg | 550 | Total Metallic input | Kg | 1105
| Sub Total | % | 15
Imported : | Hard(Aust) | % | 35
| Hard(USA) | % | 8.5 | Sinter in burden | % | 69
| Hard(BENGA) | % | 2.5
| Hard(MABU) | % | 6 |  |  |  | STEEL MELTING SHOP-III :
| LVHR(AUS) | % | 4 |  |  |  | Consumption per Tonne of Cast Steel
| LVHR(Moatize) | % | 5 |  |  |  | Hot Metal | Kg | 1017
| TUHUP | % | 1 |  |  |  | Steel scrap | Kg | 81
| Total Hard | % | 62 |  |  |  | Total Metallic input | Kg | 1098
| Soft(AUST/USA) | % | 14
| Soft(Russian) | % | 9
| Total Imported | % | 85
Grand Total
|  | % | 100
Particulars | Unit | Plan |  | Particulars | Unit | Plan | Particulars | Unit | Plan
Sp Energy | GCal/TCS | 5.86 |  | ROLLING MILLS |  |  | ROLLING MILLS
Sp Power | KWH/TSS |  |  | RAIL & STRUCTURALS MILL : |  |  | URM
Sp Water | CuM/TCS | 2.7 |  | MERCHANT MILL : |  |  | BRM
|  |  |  | Merch.Products from Billets | % | 98 | Bar & Rods from Billets | % | 97
|  |  |  | WIRE ROD MILL : |  |  | PLATE MILL :
|  |  |  | Wire rods from Billets | % | 95.2 | Fin. Plates from Slabs | % | 90